## Geral
|  |  |  | Controle de Equipamentos Offshore | [6 empty] | Equipe a bordo
|  |  |  | Sonda: | NS-56 |  | Poço: | 7-JUB-84H-ESS |  |  | Supervisor |  | RAPHAEL DELLATORRE |  | Supervisor |  | CARLOS KALEBY
[11 empty] | Técnico |  | DIEGO ROCHA |  | Técnico |  | VINICIUS PEREIRA
|  |  |  | Data: | 2026-01-20 |  | Campo: | JUBARTE |  |  | Técnico |  | EDUARDO GOMES |  | Técnico |  | ROBSON MATOS
EQUIPAMENTOS
Item | Equip. | Qtd | NP | NS | Descrição do item | Localização | Dimensões em metros (C x L x A) | Peso (Kg) | Eslinga | Solic. Material | RT de Embarque | Data de Embarque | RT de Desembarque | Data de Desembarque | Origem | Destino | Observação
1 | JUNTAS | 0 | 495094 | N/A | STRESS JOINT 43FT | N/A | - | - | N/A
2 |  | 0 | 495095 | N/A | STRESS JOINT TRANSPORT SKID | N/A | - | - | #REF!
3 |  | 0 | 495096 | N/A | MECHANICAL RAPID CONNECTOR | N/A | - | - | N/A
4 |  | 100 | 495075 | N/A | PIPE DRILL 6.5/8" - XT-MF 69 | Pipe Deck |  | - | N/A |  | 326246477 | 2026-01-10 |  |  | NS-43 | NS-56
5 |  | 1 | 495078 | NPAE-00960 | PUP JOINT 8' - XT-MF 69 | Pipe Deck |  | - | N/A
6 |  | 1 | 495078 | N/A | PUP JOINT 8' - XT-MF 69 | N/A |  | - | N/A
7 |  | 3 | 495077 | PPJ-015 / PPJ-009 / PPJ-013 | PUP JOINT 10' - XT-MF 69 | N/A |  | - | N/A
8 |  | 0 | 495077 | N/A | PUP JOINT 10' - XT-MF 69 | N/A |  | - | N/A
9 |  | 0 | 495076 | N/A | PUP JOINT 20' - XT-MF 69 | N/A |  | - | N/A
10 |  | 0 | 495076 | N/A | PUP JOINT 20' - XT-MF 69 | N/A |  | - | N/A
11 |  | 1 | 495081 | SSUB-006 | SAVER SUB BOX X BOX | Pipe Deck |  | - | N/A |  | 326245906 | 15/01/2026 |  |  | NS-43 | NS-56
12 |  | 1 | 495082 | SSUB-010 | SAVER SUB BOX X PIN | Pipe Deck |  | - | N/A |  | 326245906 | 15/01/2026 |  |  | NS-43 | NS-56
13 |  | 1 | 495083 | SSUB-015 | SAVER SUB PIN X PIN | Riser Deck |  | - | N/A |  | 326247561 | 2026-01-10
14 |  | 0 | 495106 | N/A | LUBRICATOR VALVE ASSEMBLY | N/A |  | - | N/A
15 |  | 0 | 495084 | N/A | RISER ACCESSORIES TRANSPORT BASKET | N/A |  | - | #REF!
16 | ADAPTADORES | 0 | 495097 | N/A | ADAPTER HUB 11” X RISER MC 12D | N/A |  | - | N/A
17 |  | 0 | 495098 | N/A | ADAPTER HUB 11” X RISER MC 12DX | N/A |  | - | N/A
18 |  | 0 | 495099 | N/A | ADAPTER XT-MF69 (BOX) X MC 8D (BOX) | N/A |  | - | N/A
19 |  | 0 | 495100 | N/A | ADAPTER XT-MF69 (BOX) X MC 8DX (BOX) | N/A |  | - | N/A
20 |  | 0 | 495101 | N/A | ADAPTER HUB 11” X FLANGE 11” 5X1 | N/A |  | - | N/A
21 |  | 0 | 495102 | N/A | ADAPTER HUB 11” X FLANGE 11” 4X2 | N/A |  | - | N/A
22 |  | 0 | 495103 | N/A | ADAPTER HUB 11” X FLANGE 11” 10K | N/A |  | - | N/A
23 |  | 0 | 495104 | N/A | ADAPTER HUB 11” X FLANGE 13 5/8” 5X1 | N/A |  | - | N/A
24 |  | 0 | 495105 | N/A | HUB ADAPTER TRANSPORT SKID | N/A |  | - | #REF!
25 | CROSSOVER'S | 2 | 495085 | CRO-003 CRO-001 | CROSSOVER DPR X 4 ½” IF | Pipe Deck |  | - | N/A |  | 326245906 | 15/01/2026 |  |  | NS-43 | NS-56
26 |  | 1 | 495086 | CRO-009 | CROSSOVER DPR X 6 5/8” VAM DPR SR | Pipe Deck |  | - | N/A |  | 326245906 | 15/01/2026 |  |  | NS-43 | NS-56
27 |  | 1 | 495087 | CRO-023 | CROSSOVER DPR X 6 5/8” VAM DPR HP | Pipe Deck |  | - | N/A |  | 326245906 | 15/01/2026 |  |  | NS-43 | NS-56
28 |  | 1 | 495088 | CRO-061 | CROSSOVER DPR X 6 5/8” FH | Pipe Deck |  | - | N/A |  | 326245906 | 15/01/2026 |  |  | NS-43 | NS-56
29 |  | 0 | 495089 | N/A | CROSSOVER DPR X DP 5” NC50 | Pipe Deck |  | - | N/A |  | 326245906 | 15/01/2026 |  |  | NS-43 | NS-56
30 |  | 0 | 497277 | N/A | CROSSOVER STUB ACME PIN X XT-MF69 BOX | N/A |  | - | N/A
31 |  | 0 | 497278 | N/A | CROSSOVER STUB ACME PIN X XT-MF69 PIN | N/A |  | - | N/A
32 |  | 1 | 496064 | CRO-069 | CROSSOVER DPR X SWIVEL | N/A |  | - | N/A
33 |  | 0 | 495093 | N/A | DPR CROSSOVER TRANSPORT BASKET | N/A |  | - | #REF!
34 |  | 1 | 495072 | SFTUC-002 | SFT UPPER CROSSOVER 8 ¼” STUB ACME X 8 ¼” ACME BOWEN | N/A |  | - | N/A
35 |  | 1 | 495073 | SFTUC-006 | SFT UPPER CROSSOVER 8 ¼” STUB ACME X 4 7/8” STUB ACME | Pipe Deck |  | - | N/A |  | 326245906 | 15/01/2026 |  |  | NS-43 | NS-56
36 |  | 1 | 495074 | SFTUC-012 | SFT UPPER CROSSOVER 8 ¼” STUB ACME X 9” OTIS | Pipe Deck |  | - | N/A |  | 326245906 | 15/01/2026 |  |  | NS-43 | NS-56
37 |  | 0 | 496061 | N/A | SFT UPPER CROSSOVER TEST PIN 8 ¼” STUB ACME | N/A |  | - | N/A
38 | SFT | 1 | 495070 | SFT-001 | SURFACE FLOW TREE | Riser Deck |  | - | N/A |  | 326274225 | 2026-01-13 |  |  | DPR | NS-56
39 |  | 1 | 495622 | SWJ-001 | SWIVEL JOINT | Riser Deck |  | - | N/A |  | 326274225 | 2026-01-13 |  |  | DPR | NS-56
40 |  | 1 | 495071 | TS-006 | SURFACE FLOW TREE TRANSPORT SKID | Riser Deck |  | - | N/A |  | 326245763 | 2026-01-10 |  |  | NS-43 | NS-56
41 |  | 1 | 495617 | CFP-004 | FLEXIBLE FLOW LINE PIPE ASSEMBLY | Riser Deck |  | - | N/A |  | 326245763 | 2026-01-10 |  |  | NS-43 | NS-56
42 |  | 1 | 495619 | JA-905 | FLEXIBLE FLOW LINE PIPE TRANSPORT BASKET | Riser Deck |  | - | N/A
43 |  | 1 | 496062 | PIT-009 | SWIVEL LOWER TEST BOX | Riser Deck |  | - | N/A |  | 326274225 | 2026-01-13 |  |  | DPR | NS-56
44 |  | 2 | 495623 | CWJ-004 E CWJ-005 | CASED WEAR JOINT | Riser Deck |  | - | N/A |  | 326245914 | 2026-01-10 |  |  | NS-43 | NS-56
45 | CARRETÉIS | 0 | 495016 | N/A | OPEN SEA REELER | N/A |  | - | #REF!
46 |  | 0 | 495017 | N/A | OPEN SEA UMBILICAL 38W 2000M | N/A |  | - | N/A
47 |  | 0 | N/A | N/A | PROTETOR DO CONECTOR ELÉTRICO ODI DO UEH | N/A |  | - | N/A
48 |  | 1 | 495022 | R-182 | TUBING HANGER REELER | Pipe Deck |  | - | N/A |  | 326279893 | 2026-01-13 |  |  | NS-43 | NS-56
49 |  | 1 | 495023 | U-200 | TUBING HANGER UMBILICAL 13W+HCR 2000M | Pipe Deck |  | - | N/A |  | 326279893 | 2026-01-13 |  |  | NS-43 | NS-56
50 |  | 0 | N/A | N/A | PROTETOR DO CONECTOR ELÉTRICO ODI DO UEH | N/A |  | - | N/A
51 |  | 0 | 495031 | N/A | HCR ANNULUS CIRCULATION REELER 2000M | N/A |  | - | #REF!
52 |  | 0 | 495032 | N/A | HCR ANNULUS CIRCULATION UMBILICAL 2000M X 1.1/4” | N/A |  | - | N/A
53 |  | 0 | 495031 | N/A | HCR ANNULUS CIRCULATION REELER 2000M | N/A |  | - | #REF!
54 |  | 0 | 495032 | N/A | HCR ANNULUS CIRCULATION UMBILICAL 2000M X 1.1/4” | N/A |  | - | N/A
55 |  | 0 | 495035 | N/A | HYDRAULIC ADAPTER FOR 2 HCR CONNECTION - ASSEMBLY | N/A |  | - | N/A
56 |  | 0 | 495041 | N/A | LUBRICATOR VALVE CONTROL REELER | N/A |  | - | #REF!
57 |  | 0 | 495042 | N/A | LUBRICATOR VALVE CONTROL UMBILICAL | N/A |  | - | N/A
58 | HPU / CONTROL CABIN | 0 | 495008 | N/A | HPU W/ INTEGRATED OPEN SEA CONTROL PANEL | N/A |  | - | N/A
59 |  | 0 | N/A | N/A | ELECTRICAL JUMPER HPU X RIG - POWER | N/A |  | - | N/A
60 |  | 0 | N/A | N/A | ELECTRICAL JUMPER HPU X INCLINOMETER - SIGNAL | N/A |  | - | N/A
61 |  | 0 | N/A | N/A | ELECTRICAL JUMPER HPU X OS REELER - SIGNAL | N/A |  | - | N/A
62 |  | 0 | N/A | N/A | ELECTRICAL JUMPER HPU X TH REELER - SIGNAL | N/A |  | - | N/A
63 |  | 0 | 498056 | N/A | CONTROL CABIN | N/A |  | - | N/A
64 |  | 0 | N/A | N/A | ELECTRICAL JUMPER CONTROL CABIN X RIG - POWER | N/A |  | - | N/A
65 |  | 0 | N/A | N/A | ELECTRICAL JUMPER CONTROL CABIN X RCP - POWER | N/A |  | - | N/A
66 |  | 0 | N/A | N/A | ELECTRICAL JUMPER CONTROL CABIN X RCP - COM | N/A |  | - | N/A
67 |  | 0 | N/A | N/A | ELECTRICAL JUMPER CONTROL CABIN X ESDP - SIGNAL | N/A |  | - | N/A
68 |  | 0 | N/A | N/A | ELECTRICAL JUMPER CONTROL CABIN X HPU - POWER | N/A |  | - | N/A
69 |  | 0 | N/A | N/A | ELECTRICAL JUMPER CONTROL CABIN X HPU - POWER | N/A |  | - | N/A
70 |  | 0 | N/A | N/A | ELECTRICAL JUMPER CONTROL CABIN X HPU - COM | N/A |  | - | N/A
71 |  | 0 | N/A | N/A | ELECTRICAL JUMPER CONTROL CABIN X HPU - COM | N/A |  | - | N/A
72 |  | 0 | N/A | N/A | ELECTRICAL JUMPER CONTROL CABIN X THCP - POWER | N/A |  | - | N/A
73 |  | 0 | N/A | N/A | ELECTRICAL JUMPER CONTROL CABIN X THCP - COM | N/A |  | - | N/A
74 |  | 0 | N/A | N/A | ELECTRICAL JUMPER CONTROL CABIN X THCP - COM | N/A |  | - | N/A
75 |  | 0 | 495014 | N/A | REMOTE CONTROL PANEL – RCP | N/A |  | - | N/A
76 |  | 0 | 495015 | N/A | EMERGENCY SHUTDOWN PANEL – ESDP | N/A |  | - | N/A
77 |  | 1 | 495011 | PNL-010 | TUBING HANGER CONTROL PANEL | Riser Deck |  | - | N/A |  | 326245622 | 2026-01-10 |  |  | NS-43 | NS-56
78 | JUMPER'S | 0 | N/A | N/A | JUMPER HYDRAULIC | N/A |  | - | N/A
79 |  | 0 | N/A | N/A | JUMPER HYDRAULIC | N/A |  | - | N/A
80 |  | 0 | N/A | N/A | JUMPER HYDRAULIC | N/A |  | - | N/A
81 |  | 0 | N/A | N/A | JUMPER HYDRAULIC | N/A |  | - | N/A
82 | INCLINOMETRO / JUMPER Y | 0 | 495028 | N/A | SENSOR INCLINOMETER SUBSEA DUAL | N/A |  | - | N/A
83 |  | 0 | 495029 | N/A | ELECTRICAL JUMPER CONNECTION UMBILICAL X INCLINOMETER | N/A |  | - | N/A
84 |  | 0 | 495030 | N/A | INCLINOMETER CLAMPING DEVICE ASSEMBLY | N/A |  | - | N/A
85 |  | 0 | 495021 | N/A | ELECTRICAL JUMPER 7W 14M FOR CONNECTION W/ EDP | N/A |  | - | N/A
86 |  |  | 496815 | N/A | ELECTRICAL JUMPER (Y) - OS UMBILICAL x EFL | N/A |  | - | N/A
87 | CLAMP'S | 0 | 495018 | N/A | CLAMPS TO ATTACH OS UMBILICAL TO STANDARD RISER JOINTS 6 5/8” | N/A |  | - | N/A
88 |  | 0 | 495019 | N/A | CLAMPS TO ATTACH OS UMBILICAL TO RIG RISER JOINTS 5” | N/A |  | - | N/A
89 |  | 89 | 495025 | CLP 018 | CLAMPS TO ATTACH TH UMBILICAL TO STANDARD RISER JOINTS 6 5/8” | Riser Deck |  | - | N/A |  | 326245683 | 2026-01-10 |  |  | NS-43 | NS-56
90 |  | 0 | 495026 | N/A | CLAMPS TO ATTACH TH UMBILICAL TO RIG RISER JOINTS 5” | N/A |  | - | N/A
91 |  | 1 | 495047 | 10DRY14427 | UMBILICAL CLAMP TRANSPORT BASKET | Riser Deck |  | - | N/A |  | 326245683 | 2026-01-10 |  |  | NS-43 | NS-56
92 |  | 1 | 495048 | N/A | CLAMP MAKE UP TOOL | N/A |  | - | N/A
93 | SHEAVES | 0 | 495044 | N/A | 80° SHEAVE - HCR AND LUBRICATOR VALVE UMBILICAL | N/A |  | - | N/A
94 |  | 0 | 495045 | N/A | MAIN SHEAVE - HCR UMBILICAL | N/A |  | - | N/A
95 |  | 0 | 495046 | N/A | 180º SHEAVE - HCR UMBILICAL | N/A |  | - | N/A
96 |  | 1 | 497339 | TDS-191 | MAIN SHEAVE - OS MODE UMBILICAL AND TH MODE UMBILICAL | Pipe Deck |  | - | N/A |  | 326245912 | 2026-01-10 |  |  | NS-43 | NS-56
97 |  | 1 | 497340 | TDS-195 | 180º SHEAVE - OS MODE UMBILICAL AND TH MODE UMBILICAL | Pipe Deck |  | - | N/A |  | 326245912 | 2026-01-10 |  |  | NS-43 | NS-56
98 |  | 2 | 497341 | TDS-200 ¦TDS-198 | 80° SHEAVE - OS MODE UMBILICAL AND TH MODE UMBILICAL | Pipe Deck |  | - | N/A |  | 326245912 | 2026-01-10 |  |  | NS-43 | NS-56
99 |  | 1 | 497345 | TDS-204 | 80º SHEAVE - CASED WEAR JOINT + DISPOSITIVO | Pipe Deck |  | - | N/A |  | 326245912 | 2026-01-10 |  |  | NS-43 | NS-56
100 | MANOBRA | 0 | 495049 | N/A | MAIN ELEVATOR | N/A |  | - | N/A
101 |  | 0 | 495050 | N/A | MAIN ELEVATOR TRANSPORT SKID | N/A |  | - | #REF!
102 |  | 0 | 495051 | N/A | MAIN ELEVATOR MOUNTING FRAME | N/A |  | - | #REF!
103 |  | 1 | 495052 | SBR-009 A-01 | UPPER SPREADER BAR | N/A |  | - | N/A
104 |  | 0 | 495053 | N/A | UPPER SPREADER BAR TRANSPORT SKID | N/A |  | - | #REF!
105 |  | 0 | 495054 | N/A | LONG BAILS 18M FOR SFT ELEVATOR | N/A |  | - | N/A
106 |  | 0 | 495055 | N/A | LONG BAILS TRANSPORT BASKET | N/A |  | - | #REF!
107 |  | 1 | 495056 | RS-003 | RISER SPIDER | Pipe Deck |  | - | N/A |  | 326245755 | 2026-01-10 |  |  | NS-43 | NS-56
108 |  | 1 | N/A | 20347 | RISER SPIDER CONTROL PANEL | Pipe Deck |  | - | N/A |  | 326245755 | 2026-01-10 |  |  | NS-43 | NS-56
109 |  | 1 | N/A | FG7-03 | RISER SPIDER HPU | Pipe Deck |  | - | N/A |  | 326245755 | 2026-01-10 |  |  | NS-43 | NS-56
110 |  | 1 | 495057 | MLTU 1804126 | RISER SPIDER TRANSPORT SKID | N/A |  | - | N/A |  | 326245755 | 2026-01-10
111 |  | 0 | 495058 | N/A | POWER TONG | N/A |  | - | N/A
112 |  | 0 | 495059 | N/A | POWER TONG POSITIONER | N/A |  | - | N/A
113 |  | 0 | N/A | N/A | POWER TONG LIFT CYLINDER | N/A |  | - | N/A
114 |  | 0 | 495060 | N/A | POWER TONG TRANSPORT SKID | N/A |  | - | #REF!
115 |  | 0 | 495061 | N/A | POWER TONG HPU - ELECTRICAL | N/A |  | - | N/A
116 |  | 0 | N/A | N/A | POWER TONG HPU - DIESEL | N/A |  | - | N/A
117 |  | 0 | 495065 | N/A | TORQUE-MEASUREMENT SYSTEM | N/A |  | - | N/A
118 |  | 0 | 495062 | N/A | DRILL PIPE RISER SLIPS | N/A |  | - | N/A
119 |  | 1 | 495064 | STG-020 | DPR STABBING GUIDE | N/A |  | - | N/A
120 |  | 1 | 495068 | MEL-002 | MANUAL ELEVATOR | N/A |  | - | N/A
121 |  | 0 | 495063 | N/A | THRS TRANSPORT BASKET | N/A |  | - | #REF!
122 |  | 0 | 495066 | N/A | DOUBLE DOOR ELEVATOR | N/A |  | - | N/A
123 |  | 0 | 495067 | N/A | DOUBLE DOOR ELEVATOR TRANSPORT BASKET | N/A |  | - | #REF!
124 |  | 1 | 495062 | RS-04 | DRILL PIPE RISER SLIPS 350 TON DPR 5K - CUNHA MANUAL 6.5/8¨ | N/A |  | -
125 |  | 1 | 495624 | CO-UTF3-010 | WORKSHOP CONTAINER | N/A |  | - | N/A
126 | DIVERSOS | 3 | 495069 | PIPT-010/011/003 | PIPE STAND | N/A |  | -
127 |  | 0 | 498413 | N/A | N/A | N/A |  | -
128 |  | 1 | N/A | R-16-15-26172 | SKID DE N2 | Riser Deck |  | - |  |  | 326245682 | 2026-01-10 |  |  | NS-43 | NS-56
129 |  | 1 | 495010 | HJ-006 | JUMPER 13F | Riser Deck |  | - |  |  | 326246126 | 2026-01-10
130 |  | 1 | 495013 | HJ-016 | JUMPER 10F | Riser Deck |  | - |  |  | 326246126 | 2026-01-10
131 |  | 1 | 506277 | HJ-034 | HOSE ASSEMBLY 1 IN ID X 25M LG | Riser Deck |  | - |  |  | 326246126 | 2026-01-10
132 |  | 2 | 495024 | HJ-021 ¦ HJ-019 | JUMPER HCR 1” | Riser Deck |  | - |  |  | 326246126 | 2026-01-10 |  |  |  |  | HJ-019 LOCALIZADO NA CESTA JA905 - RISER DECK
133 |  | 1 | 495027 | EJ-010 | JUMPER PDG | Riser Deck |  | - |  |  | 326246126 | 2026-01-10
#REF! |  | 1 | N/A | HJ-004 | JUMPER SFT | Riser Deck |  | - |  |  | 326246126 | 2026-01-10
#REF! |  | 1 | N/A | HDBU 0141579 | CAIXA COM QUÍMICOS | Riser Deck |  | - |  |  | 326245758 | 2026-01-10
#REF! |  | 1 | 496057 | NBP-007 | BOOSTER PUMP | Pipe Deck |  | -
#REF! |  | 1 | 504920 | CRO-050 | XO DPR XT-MF69 (CAIXA) X 6 5/8" - NC50 - PINO | N/A |  | -
#REF! |  | 0 | 616095 | N/A | XO DPR XT-MF69 X FH PINO | N/A |  | -
#REF! |  | 1 | 505091 | CRO-055 | XO DPR XT-MF69 X 6 5/8" - VAM HP PINO | N/A |  | -
#REF! |  | 1 | 539944 | PIT-015 | TEST PIN XT-MF69 | N/A |  | -
#REF! |  | 1 | N/A | TSB-003 | TEST BOX XT-MF69 - CAP 25 TON DPR 5K | Riser Deck |  | - |  |  | 326247561 | 2026-01-10
#REF! |  | 1 | N/A | N/A | PÓRTICOS (trave de sustentação das sheaves). | Riser Deck |  | -
#REF! |  | 1 | N/A | NPAE-00587 | PUP JOINT 15' | N/A |  | -
#REF! |  | 2 | 523443 | BX-001/BX-002 | INSERTO 7 1/8" PARA BX 4 | N/A |  | -
#REF! |  | 1 | 527892 | EAX-003 | ELEVATOR AUXILIAR | N/A |  | -
#REF! |  | 2 | 671862 | BS-01 ¦ BS-02 | CENTRALIZADOR | Riser Deck |  |  |  |  | 326245914 | 2026-01-10
#REF! |  | 1 | N/A | NHJU 2021132 | CONTAINER 20FT ( CWJ 5K2 ) | Riser Deck |  |  |  |  | 326245914 | 2026-01-10
#REF! |  | 1 | N/A | HDBU 0142554 | BOMBONAS DE HW | Riser Deck |  |  |  |  | 326245759 | 2026-01-09 |  |  |  |  | 9 BOMBONAS NOVAS
#REF! |  | 1 | N/A | N/A | GABARITO 5,03 | N/A
#REF! |  | 1 | 495079 | PIT-009 | TEST PIN XT-MF69 HIGH TORQUE CAP 25 TN DPR 5KII ASSEMBLY | N/A
#REF! |  | 0 | 496061 |  | SFT UPPER CROSSOVER TEST PIN 8 1/4 STUB ACME | N/A
#REF! |  | 1 | 504919 | SSUB-022 | SAVE SUB SFT | N/A
#REF! |  | 1 | N/A | HTU-3002 | TANQUE HTU | N/A |  |  |  |  | 326246129 | 2026-01-13 |  |  | NS-43 | NS-56
#REF! |  | 1 | N/A | FU-3001 | TANQUE FU | N/A |  |  |  |  | 326246129 | 2026-01-13 |  |  | NS-43 | NS-56
#REF! |  | 1 | N/A | PRJU-9703214 | CONTAINER 20FT / CONTENDO EBE | Pipe Deck
#REF! |  | 1 | N/A | LCTU-200349-5 | CONTAINER 10FT | Riser Deck |  |  |  |  | 326245912 | 2026-01-10 |  |  |  |  | CONTAINER DE SHEAVE
#REF! |  | 1 | N/A | NLTU-2001941 | CONTAINER 10FT / SSUB/TSB | N/A
#REF! |  | 1 |  | PPJ-003 | PUP 15" | Pipe Deck |  |  |  |  | 326246323 | 2026-01-13 |  |  | DPR | NS-56
#REF! |  |  |  |  | OBSERVAÇÃO: HÁ UM XO NO ESTALEIRO IMPOSSIBILITANDO REALIZAR CONFERÊNCIA DE ATIVO
#REF!
#REF!
#REF!
#REF!
Note on L11: Marcos Azeredo Mendonça - PrestServ: 1,00 x 1,00 x 1,00

## Controle de Eslingas
|  |  |  | Controle de Equipamentos Offshore | [7 empty] | Equipe a bordo
|  |  |  | Sonda: | NS-56 |  |  |  | Poço: | 7-JUB-84H-ESS |  | Supervisor |  | RAPHAEL DELLATORRE |  | Supervisor |  | CARLOS KALEBY
[5 empty] | Data teste de carga |  |  |  |  | Data da Inspeção |  | Técnico |  | DIEGO ROCHA |  | Técnico |  | VINICIUS PEREIRA
|  |  |  | Data: | 2026-01-20 |  |  |  | Campo: | JUBARTE |  | Técnico |  | EDUARDO GOMES |  | Técnico |  | ROBSON MATOS
EQUIPAMENTOS
Item | NP | NS | Descrição do item |  |  | ID Eslinga | Especificação da Eslinga | Validade da Eslinga | Data Cert. equip. / Skid | Validade teste carga equip. / skid | Localização da Eslinga |  | Solic. Material | RT de Embarque | Data de Embarque | RT de Desembarque | Data de Desembarque | Observação
1 | 495022 | R-182 | CARRETEL TH |  |  | 188157/1 |  | 2027-01-08 |  | 2027-01-06 | Pipe Deck -BE
2 | N/A | LCTU-200349-5 | CONTAINER CRO |  |  | BCE-2523906 |  | 2026-06-05 |  | 2026-06-05
3 | 432864 | HTU-3002 | UNIDADE DE POTÊNCIA HIDRÁULICA |  |  | BC-2526034 | 4 x 19mm _ 4.75T | 2026-08-05 |  | 2026-06-04 | Pipe Deck -BE |  |  | 325822423 | 2025-08-26
4 | 435631 | CO-UTF3-10 | CABINE DE CONTROLE |  |  | 569-SM | 4 x 29mm _ 12T | 2026-04-17 |  | 2026-04-17 | Pipe Deck -BE |  |  | 325822424 | 2025-08-26
5 | 420696 | FU-3001 | FU |  |  | BC-11850 | 4x 22mm_4.75T | 2026-05-05 |  | 2026-05-05 | Pipe Deck -BE |  |  | 325822423 | 2025-08-26
6 | 495011 | PNL-010 | PNL |  |  | 11326546-0-2-001 | 4 x 19mm _ 4.75T | 2026-03-21 |  | 2026-03-21 | Riser Deck |  |  | 326245622 | 2026-01-10
7 | N/A | R-16-15-26172 | SKID N2 |  |  | 104416/0018 | 4 x 19mm _ 4.75T | 2026-07-03 |  | 2026-07-04 | Riser Deck |  |  | 326245682 | 2026-01-10
8 | N/A | HDBU 0141579 | CAIXA DE QUÍMICOS |  |  | 35365-3 | 4 x 19mm _ 9,5T | 2026-04-22 |  | 2026-05-06 | Riser Deck |  |  | 326245758 | 2026-01-10
9 | N/A | NHJU2021132 | CONTAINER 20" - CWJ |  |  | NHJU-202113 |  | 30/04/2026 |  | 30/04/2026 | Riser Deck |  |  | 326245914 | 2026-01-10
10 | N/A |  | PÓRTICOS (trave de sustentação das sheaves). |  |  | N/A |  |  |  | 2026-04-16 | Pipe Deck - BE
11 | N/A | JA-533 | CESTA (JUMPER) |  |  | SES12A/00052 | 4 x 26mm _ 8.5T | 2026-07-08 |  | 09/07/206 | Riser Deck |  |  | 326246126 | 2026-01-10
12 | 495047 | 10DRY14427 | Container de CLAMPS |  |  | 10DRY14427 | 4 X 9.8m _ 10T | 2026-03-18 |  | 2026-03-18 | Riser Deck |  |  | 326245683 | 2026-01-10
14 | N/A | HDBU 0142554 | CONTAINER BOMONAS |  |  | 35372/16 | 4x29mm _ 12T | 2026-11-06 |  | 2026-11-06 | Pipe Deck - BE
13 | N/A | PRJU-9703214 | CONTAINER EBE |  |  | BC-2519226 |  | 2026-12-09 |  | 2026-12-09 | Pipe Deck - BB |  |  | 325827284 | 2025-08-28
15 | N/A | KH421 | CONTAINER SHEAVES |  |  | SOS12A/00624 | 4x26mm _ 12T | 2026-07-22 |  | 2026-07-23 | Pipe deck - BE |  |  | 326245912 | 2026-01-10
16 | N/A | DNVU2004720 | CONTAINER - CROSSOVER |  |  | 130500021 |  | 2026-08-14 |  | 2026-08-13 | Pipe Deck - BB |  |  |  | 2025-08-31
17 | N/A | JA-905 | CESTA COFLEX |  |  | SOS12A/00116 |  | 2026-05-13 |  | 2026-05-14 | Riser Deck |  |  | 326245763 | 2026-01-10
18 | N/A |  | ESLINGA DA COFLEX |  |  | L6-46081 |  | 2026-08-06 |  |  | Riser Deck |  |  | 326245763 | 2026-01-10
19 | N/A |  | ESLINGA DE DUAS PERNAS ELEVADOR AUXILIAR
20 | N/A | HDBU 0141579 | CAIXA DE QUÍMICOS |  |  | 353653 |  | 2026-04-22 |  | 2026-05-06 | Pipe deck - BE |  |  | 326245758 | 2026-01-10
21 | N/A | RS-FG7-03 | Unidade hidráulica Riser Spider |  |  | SHC-031 | 4 x 13mm _ 4.3T | 2026-07-10 |  | 2026-07-10 | Pipe Deck |  |  | 32575531 | 16/08/2025
22 | N/A | [9 empty] | Pipe Deck |  |  | 32575531 | 16/08/2025
23 | N/A | MN-4025 _ MN-5181 _ 7.188.84 | BOMBA BOOSTER (MANÔMETROS) |  |  | MN-4025 _ MN-5181 _ 7.188.84 | N/A | 2026-07-21 |  |  | Pipe Deck - BE
22 | N/A | NBP-007 | BOMBA BOOSTER |  |  |  | N/A |  |  |  | Pipe Deck |  |  | 32575531 | 16/08/2025
24 | N/A | 7-118-85 | BOMBA BOOSTER (RELIEF VALVE) |  |  |  | N/A | 2026-07-21 |  |  | Pipe Deck - BE
36 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC06 |  | 7\21/2026 |  |  | Pipe Deck
37 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC50683 |  | 2026-07-14 |  |  | Pipe Deck
38 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC05 |  | 2026-06-06 |  |  | Pipe Deck
39 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC03 |  | 2026-06-06 |  |  | Pipe Deck
40 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC62 |  | 2026-02-20 |  |  | Pipe Deck
41 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC53877 |  | 2026-07-14 |  |  | Pipe Deck
42 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC50479 |  | 2026-03-13 |  |  | Pipe Deck
43 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC67A |  | 2026-07-21 |  |  | Pipe Deck
44 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC947 |  | 2026-07-21 |  |  | Pipe Deck
45 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC15 |  | 2026-06-06 |  |  | Pipe Deck
46 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC100 |  | 2026-07-14 |  |  | Pipe Deck
47 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC2416565 |  | 2026-03-13 |  |  | Pipe Deck
48 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC-04 |  | 2026-03-13 |  |  | Pipe Deck
49 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC50495 |  | 2026-07-21 |  |  | Pipe Deck
50 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC2416440 |  | 2026-03-13 |  |  | Pipe Deck
51 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC70 |  | 2026-07-14 |  |  | Pipe Deck
52 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC38 |  | 2026-07-14 |  |  | Pipe Deck
53 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC-26 |  | 2026-07-14 |  |  | Pipe Deck
54 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC10 |  | 2026-06-03 |  |  | Pipe Deck
55 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC938 |  | 2026-07-21 |  |  | Pipe Deck
56 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC79 |  | 2026-07-14 |  |  | Pipe Deck
57 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC2416429 |  | 2026-03-13 |  |  | Pipe Deck
58 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC53922 |  | 2026-07-14 |  |  | Pipe Deck
59 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC53905 |  | 2026-03-13 |  |  | Pipe Deck
60 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC104 |  | 2026-01-27 |  |  | Pipe Deck
61 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC53919 |  | 2026-01-27 |  |  | Pipe Deck
62 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC2416568 |  | 2026-07-14 |  |  | Pipe Deck
63 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC53914 |  | 2026-07-14 |  |  | Pipe Deck
64 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC30 |  | 2026-06-06 |  |  | Pipe Deck
65 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC53895 |  | 2026-07-14 |  |  | Pipe Deck
66 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC56 |  | 2026-07-16 |  |  | Pipe Deck
67 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC928 |  | 2026-05-15 |  |  | Pipe Deck
68 | N/A |  | ESLINGA DE TUBOS DPR |  |  | 30278-NS-03 |  | 21/07/2026 |  |  | Pipe Deck
69 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC917 |  | 2026-07-14 |  |  | Pipe Deck
70 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC21 |  | 2026-07-14 |  |  | Pipe Deck
71 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC53903 |  | 2026-07-14 |  |  | Pipe Deck
72 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC14 |  | 2026-07-14 |  |  | Pipe Deck
73 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC922 |  | 2026-05-15 |  |  | Pipe Deck
74 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC2416428 |  | 2026-07-16 |  |  | Riser Deck |  |  | 326246477 | 2026-01-10
75 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC53875 |  | 2026-11-19 |  |  | Pipe Deck
76 | N/A |  | ESLINGA DE TUBOS DPR |  |  | BC94 |  | 2026-07-14 |  |  | Riser Deck |  |  | 326246477 | 2026-01-10
99 | N/A | MLTU 1804126 | CONTAINER OPEN TOP - RISER SPIDER |  |  | 27848/43 |  | 2026-05-16 |  | 2026-05-16 | Riser Deck |  |  | 326245755 | 2026-01-10
101 | N/A | MLTU 2001941 | CONTAINER - S-SUB |  |  | CM-0360 |  | 2026-11-25 |  | 2026-11-25 | Riser Deck |  |  | 326247561 | 2026-01-10
102 | N/A | TS-006 | SKID SFT |  |  | BC-19071 |  | 2026-11-07 |  | 2026-11-07 | Pipe Deck
Note on J11: Inserir exemplo: 4P x 1.1/4''x 22,3 T x 5,1 m (Quantidade de partes x Bitola x Capacidade em Toneladas x Comprimento em metros).

## Consumíveis
|  |  |  | Controle de Equipamentos Offshore |  |  |  |  | Equipe a bordo
|  |  |  | Sonda: | NS-56 | Poço: | 7-JUB-84H-ESS |  | Supervisor | RAPHAEL DELLATORRE | Supervisor | CARLOS KALEBY
[5 empty] | Data teste de carga |  |  |  | Técnico | DIEGO ROCHA | Técnico | VINICIUS PEREIRA
|  |  |  | Data: | 2026-01-20 | Campo: | JUBARTE |  | Técnico | EDUARDO GOMES | Técnico | ROBSON MATOS
EQUIPAMENTOS
Item | QNT | NP | NS |  | DESCRIÇÃO |  |  | APLICAÇÃO |  | LOCALIZAÇÃO | OBSERVAÇÃO
1 | 1 | 526315 |  |  | MOBIL GEAR 600 XP 100 |  |  |  |  | Cabine de controles
2 | 1 | 526313 |  |  | LUBRAX LITH EP2 (NLGI2) |  |  |  |  | Cabine de controles
3 | 1 | N/A |  |  | MP 507 |  |  | Uso Geral |  | Cabine de controles | Desemgraxante
4 | 1 | 524580 | N/A |  | KOPR-KOTE |  |  | Rosca XTMF-69 |  | Cabine de controles
5 | 0 | 526314 | N/A |  | TELLUS 46 |  |  |  |  | Cabine de controles | BALDE PRETO
6 | 0 | CL031-017-01 | N/A |  | WD-40 SPRAY 300ML |  |  |  |  | Cabine de controles
7 | 0 | N/A | N/A |  | LIMPA CONTATO |  |  |  |  | Cabine de controles
8 | 3 | N/A | N/A |  | ÁLCOOL ISOPROPILICO - 500ml |  |  |  |  | Cabine de controles |  |  | b
| 0 | 524242 |  |  | MARKEY VERMELHO |  |  |  |  | Cabine de controles
| 1 | N/A | N/A |  | LOCTITE 243 |  |  |  |  | Cabine de controles
| 1 | N/A | N/A |  | VG 10 |  |  |  |  | Lubrifil
| 1 | N/A | N/A |  | Óleo Padrão Pershy CS 1000 - 1L |  |  |  |  | Cabine de controles
1 | 0 | N/A | N/A |  | Protetor Solar
2 | 11 | N/A | N/A |  | HW-525 | [5 empty] | CESTA CBAD-601 _ PIPE DECK
3 | 2 | N/A | N/A |  | ENERPAC HYDRAULIC OIL HF-100 |  |  |  |  | Cabine de controles | 2L
#REF! | 0 | N/A | N/A |  | LUBRICANT TUFLUBE ALLWEATHER 18KG (ROCOL |  |  | Rolamento |  | Cabine de controles | 5Kg
#REF! | 1 | N/A | N/A |  | SACO DE TRAPO |  |  | LIMPEZA/DERRAMAMENTO |  | Cabine de controles
#REF! | 1 | N/A | N/A |  | SACO DE MANTA ABSORVENTE |  |  | LIMPEZA/DERRAMAMENTO |  | Cabine de controles
#REF! | 1 | N/A | N/A |  | LUBRAX CALCIUM GR2
#REF! | 1 | N/A | N/A |  | LUBRAX CALCIUM ECO 2
#REF! | 1 | N/A | N/A |  | MOBILGEAR SHC XMP320 SINTHETIC WIND TURBINE |  |  | ÓLEO DO MOTOR | ÓLEO DO MOTOR
#REF! | 0 | N/A | N/A |  | Óleo Hidráulico HF 101N (Enerpac) |  |  | INTENSIFICADOR | INTENSIFICADOR
#REF! | 0 | N/A | N/A |  | Óleo Hidráulico HF 100N (Enerpac) |  |  | INTENSIFICADOR | INTENSIFICADOR
#REF! | 1 | N/A | N/A |  | TELLUS S2 M
#REF! | 0 | N/A | N/A |  | PETRONAS TUTE
#REF! | 1 | N/A | N/A |  | LUBRICANT TUFLUBE ALLWEATHER 4KG |  |  | GRAXA PARA ENGRENAGEM
#REF! | 0 | 523800 | N/A |  | MOBILGEAR 636
#REF! | 0 | N/A | N/A |  | MOLYKOTE 1000 |  |  | CLAMPS
#REF! | 0 | N/A | N/A |  | OLEO NARO 32 |  |  | ENERPAC CARRETEL TH NO PARA O INTENSIFICADOR
#REF! | 0 |  |  |  | GREASE RENOLITE EP2 12.5KG TRANSLUCENT B
|  | - | -
|  | - | -
|  | - | -
|  | - | -

## Dropdown (hidden)
Opções de localização na sonda para Equipamentos | Opções de localização na sonda para Eslingas
Em operação | Bombordo
Bombordo | Booster pump
Boreste | Boreste
Cabin Control | Caixa de sobressalentes
Cabine Sondador | Control cabin
Caixa de sobressalentes | Deck de transferência
Deck de transferência | Double door elevator transport basket
Double door elevator transport basket | DPR crossover transport basket
Dpr crossover transport basket | Drill Floor
Drill Floor | Flexible flow line pipe transport basket
Flexible flow line pipe transport basket | Flying lead transport frame
Flying lead transport frame | HCR annulus circulation reeler
HPU w/ integrated open sea control panel | HPU w/ integrated open sea control panel
Hub adapter transport skid | Hub adapter transport skid
Long bails transport basket | Long bails transport basket
Main Deck | Lubricator valve control reeler
Main elevator transport skid | Main Deck
Moon Pool | Main elevator mounting frame
Pipe Deck | Main elevator transport skid
Popa | Moon Pool
Popa Bombordo | Open sea reeler
Popa Boreste | Pipe Deck
Power tong transport skid | Popa
Proa | Popa Bombordo
Proa Bombordo | Popa Boreste
Proa Boreste | Power tong transport skid
Reeler | Proa
Riser accessories transport basket | Proa Bombordo
Riser Deck | Proa Boreste
Riser spider transport skid | Riser accessories transport basket
ROV Bombordo | Riser Deck
ROV Boreste | Riser spider transport skid
Sacaria | ROV Bombordo
Sala dos Técnicos | ROV Boreste
Stress joint transport skid | Sacaria
Surface flow tree transport skid | Stress joint transport skid
THRS transport basket | Surface flow tree transport skid
Trolley | THRS transport basket
Umbilical clamp transport basket | Trolley
Upper spreader bar transport skid | Tubing hanger control panel
Workshop Container | Tubing hanger reeler
Umbilical clamp transport basket
Upper spreader bar transport skid
Workshop container

## Plan6 (hidden)
TOTAL QTY. | DESCRIPTION | PART NUMBER
3
4 | ELECTRICAL JUMPER 4 QUAD 200M FOR REMOTE DHPT READING | 0495020
4 | ELECTRICAL JUMPER 2 QUAD 200M FOR REMOTE DHPT READING | 0495027
3 | HYDRAULIC ADAPTER FOR CONNECTION 2 ANNULUS CIRCULATION LINE X STRESS JOINT | 0495037
1 | HYDRAULIC JUMPER KIT - DPR 5K | 0495012
1 | TEST DEVICES - DPR 5K | 0498235
1 | SPARE PARTS - DPR 5K | 0498236

## Mangueiras
CONTROLE DE MANGUEIRAS |  |  |  |  | Realizado por:
Sonda: | NS-43 | Dia: | 20/11/2025
Supervisor: |  | RAPHAEL DELLATORRE
ITEM | MEDIDAS | CERTIFICADO | DATA CERTIFICAÇÃO | VALIDADE | PRESSÃO DE TRAB. | OBSERVAÇÕES
HJ-034 | HOSE ASSEMBLY 1 IN ID X 25M LG | Sem identificação | Sem identificação | Sem identificação | Sem identificação | Retorno
49188 | 1/4" x 25m | 18469/2025 | 25/06/2025 |  | 18000 psi | MANGUEIRA MICROPERFURADA PARA NITROGÊNIO
MI048.77 | 1' x 25m |  | 03/09/2025 |  | 300psi | Mangueira de ar
MI048.73 | 1' x 25m |  | 03/09/2025 |  | 300psi | Mangueira de ar
MI048.74 | 1' x 25m |  | 03/09/2025 |  | 300psi | Mangueira de ar
MI048.71 | 1' x 25m |  | 03/09/2025 |  | 300psi | Mangueira de ar
MI048.78 | 1' x 25m |  | 03/09/2025 |  | 300psi | Mangueira de ar
MI048.79 | 1' x 25m |  | 03/09/2025 |  | 300psi | Mangueira de ar
MI048.80 | 1' x 25m |  | 45725 | 46090
46429 | 3/8" x 15m | 16753/2025 | 46361 | 2026-12-05 | 10.000 psi | Container de Ferramentas/Cabine
4718 | 3/8" x 15,73m | 13457/2025 | 13/02/2026 | 13/02/2026 | 5.000 psi | Container de Ferramentas/Cabine
46430 | 1/4" x 15m | 16752/2025 | 12/5/2025 | 12/5/2026 | 10.000 psi | Container de Ferramentas/Cabine
46431 | 1/4" x 15m | 16755/2025 | 12/05/2025 | 12/5/2026 | 10.000 psi | Container de Ferramentas/Cabine
47192 | 3/8" x 3,09m | 13425/2025 | 13/02/2025 | 13/02/2026 | 5.000 psi | Container de Ferramentas/Cabine
47171 | 3/8 x 3,25m | 13454/2025 | 13/02/2025 | 13/02/2026 | 5.000 psi | Container de Ferramentas/Cabine
47191 | 3/8" x 1,61m | 13458/2025 | 13/02/2025 | 13/02/2026 | 5.000 psi | Container de Ferramentas/Cabine
49612 | 1/4" 3,1m | 7850/2024 | 2024-05-09 | 2025-05-09 | 18.560 psi | Container de Ferramentas/Cabine
49623 | 1/4" x 25m | 7846/2024 | 2024-05-09 | 2025-05-09 | 18.560 psi | Container de Ferramentas/Cabine
| 1/4" x 15m | 7855/2024 | 2024-05-09 | 2025-05-09 | 10.000 psi | Container de Ferramentas/Cabine
49611 | 1/4" x 3,1m | 7851/2024 | 2024-05-09 | 2025-05-09 | 18.560 psi | Container de Ferramentas/Cabine
| 1/4" x 3,1m | 7852/2024 | 2024-05-09 | 2025-05-09 | 18.560 psi | Container de Ferramentas/Cabine
49615 | 1/4'' 15 m |  | 2024-05-09 | 2025-05-09 | 18.560 psi | Container de Ferramentas/Cabine
48731-4 | 1 "x 25m | 12012/2024 | 45942 | 10/12/2025 | 150 psi | Mangueira de Ar. Container de Ferramentas/Cabine

## EQP. MEDIÇÃO
|  |  |  | Controle de Equipamentos Offshore | [7 empty] | Equipe a bordo
|  |  |  | Sonda: | NS-43 |  |  |  | Poço: | 7-RO-190H-RJS |  | Supervisor |  | RAPHAEL DELLATORRE |  | Supervisor
[5 empty] | Data teste de carga |  |  |  |  | Data da Inspeção |  | Técnico |  | YASMIN FERREIRA |  | Técnico
|  |  |  | Data: | 2025-11-09 |  |  |  | Campo: | JUBARTE |  | Técnico |  |  |  | Técnico
EQUIPAMENTOS
Item | NP | NS | Descrição do item |  |  | ID Eslinga | Especificação da Eslinga | Validade da Eslinga | Data Cert. equip. / Skid | Validade teste carga equip. / skid | Localização da Eslinga |  | Solic. Material | RT de Embarque | Data de Embarque | RT de Desembarque | Data de Desembarque | Observação
26 | N/A | TDR-STR-0004 | TDR | [5 empty] | 2026-05-16 |  | Pipe Deck
27 | N/A | MT-04 | MULTIMETRO | [5 empty] | 2025-12-09 |  | Riser deck
28 | N/A | MT-15 | MULTIMETRO | [5 empty] | 2026-05-07
29 | N/A | ME-34 | MEGÔMETRO | [5 empty] | 2026-04-18 |  | Riser deck
30 | N/A | ME-09 | MEGÔMETRO | [5 empty] | 2026-08-12
31 | N/A | TQ-15 | TORQUÍMETRO para CWJ | [5 empty] | 2025-12-17 |  | Pipe Deck
32 | N/A | TQ-38 | TORQUIMETRO 40-200 N.m | [5 empty] | 2025-08-20 |  | Pipe Deck
33 | N/A | PQ-10 | PAQUÍMETRO | [5 empty] | 2025-08-16 |  | Pipe Deck
34 | N/A | PQ-19 | PAQUÍMETRO | [5 empty] | 2025-08-29 |  | Pipe Deck
35 | N/A | PQ-09 | TORQUÍMENTRO DO KIT CLAMPS (TLCMP-007) | [5 empty] | 21/08/2026 |  | Pipe Deck
| LEGENDA: |  | 60 DIAS OU MAIS PARA O VENCIMENTO
MENOS DE 60 DIAS PARA O VENCIMENTO
VENCIDO
Note on J11: Inserir exemplo: 4P x 1.1/4''x 22,3 T x 5,1 m (Quantidade de partes x Bitola x Capacidade em Toneladas x Comprimento em metros).